## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US0.1 | Log in to the system and access the corresponding function page | As a system user, I want to be able to log into the system and enter the function page corresponding to my role, so that I can safely access the functions I need. | Must have | 1 | 1. System users can log in to the system using their registered username and password. 2. When both the username and password are correct, the system should allow login success and direct the user to the function page corresponding to their role. 3. The system supports at least 3 types of roles for login: Teaching Assistant Applicant (TA), Module Owner (MO), and Administrator (Admin). 4.Upon successful login, a Teaching Assistant Applicant should be directed to the applicant function page; a Module Owner should be directed to the position management page; and an Administrator should be directed to the management page. 5. If the username does not exist or the password is incorrect, the system should give a clear prompt and deny login. 6. If the username or password is empty, the system should prompt that required information is incomplete and deny login. 7. After a successful login, the system should only allow users to access functions corresponding to their role, not directly enter other roles' pages. 8. User account information and role information should be read from the system data file and remain consistent for subsequent logins. | 3 |  | 2026-03-23 | 2026-03-30
Epic1: Complete the full teaching assistant position application process and ensure convenient application operations without invalid actions.
US1.1 | Create application materials | As a teaching assistant applicant, I want to be able to create a personal profile and upload my resume, so that I can complete the preparation of materials before applying. | Must have | 1 | 1. Teaching Assistant Applicants can create personal application materials and fill in required information: name, student ID, and contact information. 2. Applicants can upload 1 resume as part of the personal application materials. 3. The system only accepts resume files in PDF format. 4. The resume file size must not exceed 10MB. 5. If the required information is not filled out completely, the system should prompt for missing items and prevent saving as complete application materials. 6. If the uploaded resume format does not meet the requirements, or the file size exceeds the limit, the system should give a clear prompt and prevent saving as complete application materials. 7. Upon successful saving, the system should display a success prompt; when the applicant re-enters the personal information page, they should be able to view the saved materials and resume upload status. 8. The saved personal information and resume-related information should be written into the system data file and read correctly upon subsequent access. | 5 |  | 2026-03-30 | 2026-04-06
US1.2 | Update application materials | As a teaching assistant applicant, I want to be able to modify my personal profile and update my resume, so as to ensure that the application information submitted is up-to-date and accurate. | Should have | 2 | 1. Teaching Assistant Applicants can view their saved personal application materials. 2. Applicants can modify existing content in their personal materials and replace the current resume. 3. The system only retains 1 current effective resume at any time; after uploading a new resume, the status of the old resume should be updated to replaced or no longer as the current version. 4. During an update, the system still requires that the required information remains complete: name, student ID, and contact information cannot be empty. 5. The newly uploaded resume must still be in PDF format and the size must not exceed 10MB. 6. If the required information after modification is incomplete, or the new resume does not meet the format/size requirements, the system should give a clear prompt and prevent saving the updated materials. 7. After a successful update, the system should display a success prompt and show the latest saved material content and current resume status. 8. The updated materials should overwrite the original valid version and be written into the system data file; when the applicant enters the personal information page again, they should see the latest version. 9. The system only allows applicants to view and modify their own personal materials and does not allow modifications to other users' materials. | 3 |  | 2026-04-13 | 2026-04-27
Epic2: Quickly obtain matching positions and track application status, improving application efficiency and transparency.
US2.1 | Browse teaching assistant positions | As a teaching assistant applicant, I want to be able to browse the currently open teaching assistant positions, so that I can find suitable job opportunities for myself. | Must have | 1 | 1. Assistant applicants can view the list of current open teaching assistant positions. 2. Each position list information should display at least: position name, job type, application deadline, position status. 3. When there are no open positions, the system should display a clear message, such as 'No positions available for application'. 4. After clicking on a position, assistant applicants should be able to enter the details page of that position. 5. The position list data should be read from the system data file and kept consistent with the current saved position status. | 3 |  | 2026-05-18 | 2026-05-25
US2.2 | View job details | As a teaching assistant applicant, I want to be able to view the detailed information of positions, so that I can judge whether the position meets my abilities and time arrangements. | Must have | 1 | 1. Assistant applicants can view the detailed information of a specific position. 2. The position details page should display at least: position name, position description, required skills, work time/schedule, application deadline, position status. 3. When the position is still open, the details page should provide an 'apply' option. 4. When the position is closed or the deadline has passed, the details page should clearly indicate 'not applicable' status and disable the apply option. 5. After returning to the position list from the details page, the system should retain the original browsing results rather than jumping back to a blank page. | 2 |  | 2026-03-30 | 2026-04-02
US2.3 | Filter jobs by criteria | As a teaching assistant applicant, I want to be able to filter the teaching assistant positions, so that I can find a position that matches my own conditions more quickly. | Could have | 4 | 1. Assistant applicants can filter positions based on one or multiple conditions. 2. The filtering conditions supported by the system should include at least: position status, application deadline. 3. After selecting one or more filtering conditions, the position list should only display results that match the conditions. 4. When no positions meet the filtering conditions, the system should display a clear message, such as 'No positions found that match the conditions'. 5. Assistant applicants can clear the selected filtering conditions with one click and restore the display of all open positions. 6. The filtering results should be generated based on the position information in the current system data file. | 2 |  | 2026-04-27 | 2026-05-15
US2.4 | Submit job application | As a teaching assistant applicant, I want to be able to submit an application for a teaching assistant position, so as to strive for the job opportunities I want. | Must have | 1 | 1. Assistant applicants can only submit a position application if they have completed their personal application information and uploaded a current valid resume. 2. Assistant applicants can submit applications for positions that are open and have not passed the deadline. 3. When submitting an application, the system should record at least: applicant identity, position applied for, application time, application status. 4. After a successful application submission, the system should display a clear success message. 5. After a successful application submission, the initial status of that application should be set to 'awaiting review'. 6. Submitted application records should be written into the system data file and visible on the application history or application status page. 7. The system should prevent application submission and provide a clear prompt when the position is closed, the deadline has passed, or the applicant's information is incomplete. | 5 |  | 2026-05-18 | 2026-05-25
US2.5 | Withdraw submitted application | As a teaching assistant applicant, I want to be able to withdraw a submitted position application, so as to give up positions that are no longer suitable for myself. | Should have | 2 | 1. Assistant applicants can only withdraw their applications that have been submitted and are currently in the 'pending review' status. 2. When the application status has become 'accepted' or 'rejected', the system does not allow for the withdrawal of that application. 3. After the assistant applicant confirms the withdrawal, the system should update the application status to 'withdrawn'. 4. Upon successful withdrawal, the system should display a clear prompt, and the application should no longer be shown as a current valid application. 5. After withdrawal, the application record should still be retained in the system and visible in the application history. 6. The status change after withdrawal should be written into the system data file and correctly read during subsequent access. | 2 |  | 2026-06-08 | 2026-06-22
US2.6 | Prevent duplicate applications for the same position | As a teaching assistant applicant, I hope the system can prevent me from repeatedly applying for the same teaching assistant position and give a clear prompt, so as to avoid application status confusion caused by accidental operations or network delays. | Should have | 2 | 1. The system should not allow an assistant applicant to submit another application for the same position if there is already 1 current valid application record for that position. 2. Current valid application records at least include applications with the status of 'pending review' or 'accepted'. 3. When the applicant repeatedly clicks the application button for the same position, the system should give a clear prompt, such as 'You have already applied for this position'. 4. With the existence of valid application records, the application button on the position details page should be disabled, or the submission cannot be completed again. 5. The duplicate check should be executed before formally writing the application record to avoid multiple identical application records due to repeated clicks or network delays. | 3 |  | 2026-06-15 | 2026-06-29
US2.7 | Favorite jobs and apply quickly | As a teaching assistant applicant, I want to be able to bookmark interesting teaching assistant positions and quickly initiate applications from the bookmark list later, so as to centrally manage my position choices and reduce repeated searches. | Could have | 4 | 1. Assistant applicants can add interesting positions to their favorites list, or remove positions from the favorites list. 2. The favorites list should at least display: position name, module/activity, application deadline, position status. 3. Assistant applicants can directly enter the position details page from the favorites list, or initiate a position application. 4. When the position is closed or past the deadline, it can still be displayed in the favorites list, but should be clearly marked as 'not applicable'. 5. When the applicant already has a valid application record for the position, the quick application entry in the favorites list should be disabled, and a prompt should be given. 6. Favorite data should be written into the system data file and still be readable when the applicant logs in again later. | 3 |  | 2026-05-11 | 2026-06-05
Epic3: Complete teaching assistant position publishing and management, avoid position information errors and invalid applications.
US3.1 | Check application status | As a teaching assistant applicant, I want to be able to view the current status of each position application, so as to timely understand the application progress and results. | Must have | 1 | 1. Assistant applicants can view the current status of all positions they have applied for. 2. In the application status list, each record should at least display: position name, submission time, current status. 3. The system supports displaying application statuses including: pending review, accepted, rejected, withdrawn. 4. When the status of an application changes, upon the applicant's next visit to the status page, the latest status should be visible. 5. When the applicant currently has no application records, the system should display a clear prompt, such as 'No application records'. 6. The system only allows applicants to view their own application statuses, not those of other users. 7. Application status information should be read from the system data file and remain consistent with the currently saved application records. | 2 |  | 2026-03-23 | 2026-03-30
US3.2 | View application history | As a teaching assistant applicant, I want to be able to view my historical application records, so as to review past application situations and manage subsequent application plans. | Should have | 3 | 1. Assistant applicants can view their historical application records for a review of past application situations. 2. Each record in the application history should display at least: job title, submission time, and final status. 3. Ended application records, including those that have been accepted, rejected, or withdrawn, should be retained in the historical records. 4. Assistant applicants can distinguish between current ongoing applications and ended applications in the history. 5. When an applicant has no historical application records, the system should display a clear prompt, such as 'No historical application records'. 6. The history record page should display a maximum of 10 records per page; when the number of records exceeds 10, the system should support paging or continue viewing subsequent records. 7. The system only allows applicants to view their own historical application records and does not allow viewing of other users' historical data. 8. The historical application records should be saved in the system data file and can be correctly read when the applicant logs in again later. | 2 |  | 2026-05-11 | 2026-06-02
Epic4: Manage teaching assistant positions throughout their lifecycle
US4.1 | Create teaching assistant position | As a module leader, I want to be able to create a teaching assistant position, so as to publish position information and receive applications. | Must have | 1 | 1. Module leaders can create a new teaching assistant position and fill in the required information. 2. Required information at least includes: job title, job description, application deadline, and number of positions. 3. The number of positions must be a positive integer greater than 0. 4. The application deadline must not be earlier than the position creation date. 5. When any required information is missing, the system should prompt the missing items and prevent the position from being published. 6. When the number of positions is illegal, or the application deadline is illegal, the system should give a clear prompt and prevent the position from being published. 7. After the position is successfully published, the system should display a success prompt and set the status of the position to 'open'. 8. The newly created position should be written into the system data file and can be seen by teaching assistant applicants in the position list. 9. The system only allows module leaders to create and publish positions and does not allow teaching assistant applicants to perform this operation. | 5 |  | 2026-03-30 | 2026-04-06
US4.2 | Edit teaching assistant position | As a module leader, I want to be able to edit the teaching assistant position information, so as to update the position requirements and related arrangements in a timely manner. | Should have | 3 | 1. Module leaders can view and edit the information of the teaching assistant positions they have created. 2. Editable content should include at least: job description, required skills, work time/schedule, application deadline, and number of positions. 3. When the position still has no application records, the module leader can modify all position information. 4. When the position already has application records, the system still allows modification of non-core information, but does not allow modification of core information that would affect the validity of the application. 5. Core information in this system at least includes: job title. 6. After editing, the number of positions must still be a positive integer greater than 0, and the application deadline must not be earlier than the current date. 7. When the modification content does not meet the requirements, the system should give a clear prompt and prevent saving. 8. After successful modification, the system should display a success prompt and display the latest content in the job details. 9. The updated position information should overwrite the original valid version and be written into the system data file; the latest version should be displayed when accessed later. 10. The system only allows module leaders to edit the positions they have published and does not allow editing of positions created by other users. | 3 |  | 2026-05-19 | 2026-06-05
US4.3 | Close teaching assistant position | As a module leader, I want to be able to close the teaching assistant position, so as to stop receiving new position applications. | Should have | 3 | 1. Module leaders can perform the closure operation on teaching assistant positions that they have created and which are currently in the 'open' status. 2. Before closing a position, the system should require the module leader to confirm once to avoid accidental operations. 3. After the position is successfully closed, the system should display a success message and update the status of the position to 'closed'. 4. After the position is closed, teaching assistant applicants can still view the position information, but the system should clearly mark it as 'not applicable for application'. 5. After the position is closed, the system should no longer accept new position applications, and the application entry should be disabled. 6. The closure operation should not delete the existing application records for the position; the existing applications should still be retained for future review and approval. 7. The status changes of the closed position should be written into the system data file and should be correctly read during subsequent access. 8. The system only allows module leaders to close positions they have published and does not allow them to close positions created by other users. | 2 |  | 2026-05-19 | 2026-06-10
Epic5: Efficiently screen and manage TA applicants, reduce manual review workload.
US5.1 | View job application list | As a module leader, I want to be able to view the application list of a certain teaching assistant position, so as to quickly understand who the current applicants are for that position. | Must have | 1 | 1. Module leaders can view the application list for a teaching assistant position they have published. 2. In the application list, each record should display at least: applicant's name, student number, submission time, current status. 3. The application list defaults to only showing application records related to the current position and should not mix in applications for other positions. 4. The application list should display a maximum of 10 records per page; when there are more than 10 records, the system should support paging or viewing subsequent records. 5. When a position currently has no applications, the system should display a clear message, such as 'No application records'. 6. Module leaders can enter the detail page of a single applicant from the application list. 7. The application list information should be read from the system data file and should be consistent with the currently saved application records. 8. The system only allows module leaders to view the application list for positions they have published and does not allow them to view the application data for positions published by other users. | 3 |  | 2026-04-06 | 2026-04-13
US5.2 | View applicant details and resumes | As a module leader, I want to be able to view the personal profile and resume of a single applicant, so as to evaluate whether their background meets the job requirements. | Must have | 2 | 1. Module leaders can view the application details submitted by a specific applicant for the current position. 2. The detail page should at least display: applicant's name, student number, contact information, personal data summary, application position, submission time, current status. 3. Module leaders can view the resume file or resume content summary submitted by the applicant. 4. When the applicant has not successfully uploaded a resume, the system should give a clear prompt instead of displaying a blank page. 5. After module leaders return to the application list from the detail page, the system should retain the original position's application list instead of jumping back to the initial page. 6. The applicant's details and resume information should be read from the system data file and should be consistent with the currently saved data. 7. The system only allows module leaders to view the details of applicants related to their own positions and does not allow access to application data unrelated to their positions. | 3 |  | 2026-04-06 | 2026-04-27
US5.3 | Sort application list by match score | As a module leader, I want to be able to sort the application list, so as to quickly identify applicants who are more suitable for the position. | Want to have | 4 | 1. The module leader can sort the application list for a position by matching score. 2. The matching score sorting should be based on a comparison between the job requirements and the relevant information in the applicant's data, considering at least: required skills, relevant experience, available time/hours arrangement. 3. The system should generate a matching score result for each applicant and display them in order from highest to lowest. 4. When two applicants have the same matching score, the system should sort them by the time of application submission from earliest to latest. 5. The module leader can switch between viewing results in 'default order' and 'sorted by matching score'. 6. When the number of applicants for a position is less than 2, the system can still display the matching score results, but the sorting function should not malfunction. 7. The matching score sorting results are for reference only and should not automatically change the application status. 8. The sorting results should remain consistent with the current position and current applicant data. | 8 |  | 2026-06-15 | 2026-07-15
US5.4 | Review applications and update status | As a module leader, I want to be able to review applicants and update their application status, so as to complete the selection process for the position. | Must have | 2 | 1. The module leader can review applications for their own positions that are in the 'under review' status. 2. The module leader can update the application status to 'accepted' or 'rejected'. 3. When the application status is already 'accepted', 'rejected', or 'withdrawn', the system should not allow for review through the under review process again. 4. After a successful status update, the system should display a clear prompt and show the latest status in the application list. 5. After the status update, the applicant should also be able to see the latest result on their application status page. 6. The review results should be written into the system data file and be correctly read upon subsequent access. 7. The system only allows the module leader to review applications for positions they posted and does not allow the modification of application statuses for other users' positions. | 5 |  | 2026-04-06 | 2026-04-20
US5.5 | Automatically send review result notifications | As a module leader, I want the system to automatically send notifications to applicants once the review results are determined, to reduce repetitive communication and inform them of the results promptly. | Could have | 3 | 1. When the module leader updates the application status to 'accepted' or 'rejected', the system should automatically generate the corresponding notification. 2. The notification content should include at least: applicant's name, position name, review result. 3. The same status update operation should generate only 1 corresponding notification to avoid duplication. 4. When the review result has not changed, the system should not generate a new notification. 5. When the applicant enters the system again, they should be able to see the latest review notification related to themselves. 6. Notification records should be written into the system data file and be correctly read upon subsequent access. 7. The system should only display the review result notification to the corresponding applicant and not to other users. | 3 |  | 2026-06-02 | 2026-06-23
US5.6 | Export list of accepted applicants | As a module leader, I want to be able to export the list of selected applicants by module, for subsequent personnel allocation, communication, or record keeping. | Could have | 3 | 1. The module leader can export a list of applicants with the status 'hired' for a specific position. 2. The exported list should at least include: applicant's name, student ID, contact information, position name, and final status. 3. If there are no hired applicants for a position, the system should give a clear prompt, such as 'No exportable list of hired applicants available'. 4. The exported file format should be CSV, to meet the project's requirement for using simple text files. 5. Each export should only include hired applicants for the currently selected position and should not mix in data from other positions. 6. Upon successful export, the system should display a success message and generate a downloadable list file. 7. The system only allows the module leader to export the hiring list of positions they have posted and does not allow exporting data from positions posted by other users. | 2 |  | 2026-06-02 | 2026-06-25
Epic6：实现全局账号与工作量管理，保障 TA 工作分配均衡与系统安全
US6.1 | Set application quantity limits | As an administrator, I want to be able to set the maximum number of applications each teaching assistant applicant can submit, to control the scale of applications and ensure fairness in distribution. | Should have | 3 | 1. Administrators can set the maximum number of applications a teaching assistant applicant can submit. 2. The upper limit for the number of applications allowed should be an integer greater than 0. 3. If the administrator has not set a limit, the system should use a default limit; a default value can be set to 3 position applications. 4. When an applicant has reached the application limit, the system should prevent them from submitting new position applications and provide a clear prompt. 5. Applicants who have reached the limit can still view job information but cannot successfully submit new applications. 6. When an applicant cancels a currently valid application, the system should recalculate their number of applications. 7. The application quantity limit rules should be written into the system data file and correctly read during subsequent access. 8. The system only allows administrators to set or modify application quantity limits and does not allow other roles to perform this operation. | 3 |  | 2026-04-22 | 2026-05-15
US6.2 | View overall workload of TAs | As an administrator, I want to be able to view the overall workload of teaching assistants, to identify imbalances in work distribution and support subsequent coordination. | Must have | 2 | 1. Administrators can view the current overall workload information for each teaching assistant. 2. Each record in the workload list should at least show: teaching assistant's name, student ID, number of currently hired positions, and estimated total hours. 3. The system should only count positions with the status 'hired' towards the overall workload and not include applications with statuses 'under review', 'rejected', or 'withdrawn'. 4. If a teaching assistant currently has no hired positions, the system should display their position count as 0 and estimated total hours as 0. 5. Administrators can view the overall workload of a specific teaching assistant by name or student ID. 6. When a teaching assistant's estimated total hours exceed the team's set threshold, the system should mark it prominently; a default threshold of 20 hours/week can be used. 7. Workload information should be automatically generated based on current position assignment data and remain consistent with the hiring results in the system data file. 8. The system only allows administrators to view all teaching assistants' overall workloads and does not allow regular applicants to view others' workload information. | 5 |  | 2026-04-06 | 2026-04-20
US6.3 | View hiring and assignment status | As an administrator, I want to be able to view the hiring and allocation situation of each module, to understand the results of personnel configuration and identify modules that need adjustments. | Should have | 3 | 1. Administrators can view the recruitment and allocation status of each module or activity. 2. The allocation list should display at least: module/activity name, position name, number of people recruited, total number of positions, and remaining vacancies. 3. The system should automatically calculate the remaining vacancies based on the total number of positions and the number of people recruited. 4. When no one has been recruited for a position, the system should show the number of people recruited as 0. 5. When a position is fully recruited, the system should clearly mark the position as 'Fully Recruited' or an equivalent status. 6. Administrators can view the allocation of all positions within at least one module/activity, as well as the overall allocation summary. 7. Recruitment and allocation information should be generated from the current position and application status data, and should remain consistent with the system data files. 8. The system only allows administrators to view the overall recruitment and allocation status; it does not permit regular applicants to access this page. | 3 |  | 2026-04-22 | 2026-05-15
US6.4 | View recruitment statistics | As an administrator, I want to be able to view the statistics of job postings, applications, and hiring for each module, to oversee the recruitment progress as a whole. | Could have | 4 | 1. Administrators can view the recruitment statistics of the system for overall monitoring of recruitment progress. 2. The statistics should include at least: total number of positions, number of open positions, total number of applications, number of people recruited, and number of people rejected. 3. The system should support viewing statistics by module/activity dimension. 4. The system should support viewing the statistics of a single module/activity, as well as the overall statistical summary. 5. When a module currently has no positions or no application records, the system should display the corresponding statistical value as 0, not blank. 6. The statistics should be automatically generated based on the current system data file's position and application data and reflect the latest results after data changes. 7. The system only allows administrators to view recruitment statistics and does not permit regular applicants or module leaders to view the overall statistics page. | 3 |  | 2026-06-02 | 2026-07-02